Event Planning SOP

Purpose

Run professional in-person events in The Forge format — half-day, TED Talk-style, with full content capture — and systematically turn every event into months of content output.

When to Use

Planning a new Forge event or similar in-person gathering

Dennis requests a recurring event series

An opportunity arises for a multi-speaker, content-rich event

Preparing post-event content processing pipeline

Process

Define the event. Lock down: date, city, venue, format (half-day TED Talk-style), target audience, number of speakers (9 standard), and talk duration (20 minutes each). Document everything in a Basecamp project.

Secure the venue. Requirements: capacity for audience + crew, AV equipment (projector, screen, mics), access to or proximity to a podcast studio, green screen studio if possible. Confirm venue availability and book with deposit.

Send speaker invitations. Email each speaker with:

What The Forge is (half-day event, 9 speakers, TED Talk format)

What they'll present (their topic, 20-minute slot)

Logistics (date, time, location, travel details)

What they get (professional recording, content package, exposure)

What you need from them (bio, headshot, talk title, slides if applicable)

Confirm all speakers by deadline. Set the confirmation deadline at 2 weeks before promotion starts. No confirmed speaker = find a replacement immediately. Maintain a backup speaker list.

Book travel. Use points when possible. Budget airlines (Frontier, Spirit) for cost-sensitive bookings. Book flights and hotels at least 3 weeks out. Track all travel expenses for the P&L.

Plan content capture. Gear checklist:

Multiple cameras (minimum 2 angles per speaker)

Lapel mics or podium mic with backup

Podcast studio access for interview sessions during breaks

Green screen studio for speaker intros/outros

B-roll equipment (handheld camera, gimbal)

Execute event-day logistics.

Arrive 30 minutes before first speaker

Print the schedule and post it visibly

Name badges for all attendees and speakers

Full AV check before doors open (test mics, cameras, projector, recording)

Assign someone to manage time — strict 20-minute limit per speaker

Run the event format.

20 minutes per speaker, no exceptions

Networking breaks between speaker blocks

Podcast interviews with speakers during breaks (pre-schedule these)

Group dinner after the event for relationship building

Process post-event content. Turn raw footage into:

Full YouTube talks (one per speaker)

Book chapters (from talk transcripts)

Podcast episodes (from break interviews)

Speaker highlight reels (90-second cuts)

Short-form clips for Instagram Reels, YouTube Shorts, TikTok, LinkedIn

Boost content via Dollar-a-Day. Run $1/day campaigns on the best-performing clips. Tag speakers. Cross-promote across all channels. See dollar-a-day-campaign.md for the full process.

Document learnings for next event. Within one week of the event, write a debrief: what worked, what didn't, what to change. Update this SOP with findings. Dennis wants this recurring — every event should be better than the last.

Quality Checks

☐ All speakers confirmed with bios, headshots, and talk titles

☐ Travel booked for all out-of-town participants

☐ AV equipment tested day-of before doors open

☐ Content capture equipment ready with backups (batteries, cards, backup recorder)

☐ Post-event content processing timeline set with deadlines and owners

Common Pitfalls

Not enough cameras or angles. One camera = one angle = boring content. Plan for minimum 2 angles. Three is better.

Poor audio in the venue. Test mics in the actual room. Venue acoustics vary wildly. Bring a backup audio recorder (Zoom H6 or similar).

Speakers going over time. 20 minutes means 20 minutes. Assign a timekeeper. Use a visible countdown timer. Brief speakers beforehand — going over steals time from the next person.

No post-event content plan. The event is the raw material, not the deliverable. If you don't have a processing plan before the event, the footage sits unused. Assign owners and deadlines before event day.

Not promoting the output. Recording content and not distributing it is wasted effort. Every talk should become at least 5 pieces of content, boosted via Dollar-a-Day.

Canon Compliance

Canon source: 02-content-factory-process.md

Triangles served: ACC (content from events), CCS (process checklist for event execution)

Human checkpoints: Speaker confirmation (Step 4), AV check before doors open (Step 7), post-event debrief (Step 11)

Anti-vandalism: Backup speaker list maintained; backup AV equipment required; content processing plan required before event day; post-event debrief within one week

Last audited: 2026-03-20 (BlitzMetrics Canon Alignment run)

Learnings Log

2026-03-18: SOP created for The Forge (April 8, 2026) — first in-person event since COVID. 9 speakers, 20 min each, half-day format. Dennis wants this recurring.