Knowledge Panel Sprint — Delivery SOP

Purpose

This SOP defines exactly how we deliver a Knowledge Panel Sprint: what's included, what's not, who does what, how they're paid, and what "done" looks like. Claude should reference this for any Sprint-related work — client onboarding, project management, content production, QA, or team coordination.

When to Use

Starting a new Knowledge Panel Sprint engagement

Onboarding a qualified DFY client

Managing Sprint delivery timelines

Assigning and tracking Sprint tasks

Running QA passes on deliverables

Calculating team compensation on a Sprint

Creating case studies from completed Sprints

The Product

Knowledge Panel Sprint — $6,000, 30 days, fixed scope, zero custom detours.

Payment Terms

50% to start, 50% on delivery

Clock pauses if client blocks prerequisites

No custom work inside Sprint — extra wants = Phase 2 after delivery

Qualification Gate

LSA category business

$100k+/mo revenue

100+ 5-star reviews

Willing to film

Fixed Deliverables

1. Personal Brand Site (live, templated theme)

Entity-first architecture: Home, About, Media/Press, Speaking, Services, Contact

schema.org Person/Organization + social/knowledge graph linking

Citation hub with outbound links to verified profiles and press

2. Entity Foundations

10-20 citations/mentions cleaned and published (associations, press, directories)

Unified NAP/handles + indexable profiles

3. Authority Content

1 recorded interview (60 min) → 3 authority articles (edited/SEO'd)

6 short-form videos (subtitled, branded, hooks + CTAs)

4. Distribution Mini-Plan

Posting plan + Dollar-a-Day starter plan and budget map

5. Entity Health Snapshot

"Panel likelihood" score + checklist of next moves

30-Day Delivery Process

Day 0-2: Intake & Prerequisites

Send intake checklist to client (brand assets, bios, accounts)

Collect all prerequisites

Set up project in Basecamp/PM tool

Confirm interview date

Day 3-7: Foundation

Site scaffold built on templated theme

Schema markup implemented (Person/Organization)

Interview scheduled and recorded (60 min)

Begin citation research

Day 8-20: Production

3 authority articles written from interview transcript (edited, SEO'd)

6 short-form videos produced (subtitled, branded, hooks + CTAs)

10-20 citations cleaned and published

Profiles unified (NAP/handles)

Internal linking completed

Day 21-26: QA & Distribution Setup

Technical QA passes on site, schema, citations

Distribution plan finalized

Dollar-a-Day starter plan and budget map created

All deliverables reviewed against checklist

Day 27-30: Handoff

Client review of all deliverables

Fixes applied

Entity Health Snapshot generated

Next-step plan delivered

Case study drafted from engagement

Client Must-Dos

Provide brand assets, bios, account access on time

Attend 60-min interview

Approve copy quickly (delays pause the clock)

Team Roles & Compensation (Per $6,000 Sprint)

Role-based. Paid on collected cash.

Sales Commission (Closer): 15% — $900

Paid to the person who sourced AND closed the deal

Requires CRM evidence: lead source, call notes, proposal sent, signature

Dennis is default closer unless another closer is recorded

Delivery Lead (PM): 10% — $600

Paid on on-time delivery (<=30 days)

If late due to documented client delay, still payable

Sam McLeod is default; assigned PM earns this if Sam is not on the project

Delivery Labor Pool: 35% — $2,100

Budget for writers, editors, designers, VAs

Paid by task per SOP rate card (per article, per clip, per citation block)

Sam allocates; Dennis approves exceptions

QA/On-Time Bonus Pool: 5% — $300

Released ONLY if project ships on time with zero critical defects

Split among team members who passed QA on their tasks

Company Retained Margin: 35% — $2,100

Covers ops, software, R&D (LSS), runway

BD KPI Gate (Jack or anyone in BD role)

Minimum activity: 10 qualified intros/week OR 4 closes/month AND >=70% show rate

Miss two consecutive months → BD role paused (no commissions) until re-approved

Vacation >7 consecutive business days → reassign owned opps

Governance & Cadence

Weekly Standup (Tuesdays, 30 min)

Pipeline: new leads, proposals out, closes

Delivery: red/amber/green per project vs. Day 30

Scoreboard (public)

Closes this week/month

On-time delivery %

Defect rate

Client CSAT

Case studies shipped

Boundaries

No new services, pilots, or detours for 90 days — requests go to Phase 2 list

Every Sprint yields a published case study — if it's not published, it's not done

SOPs and checklists must be followed for comp eligibility

Quality Checks

All 5 deliverable categories complete before handoff?

Schema markup validates (test with Google Rich Results Test)?

All citations live and indexable?

Articles pass E-E-A-T standards?

Short-form videos have subtitles, branding, hooks, and CTAs?

Dollar-a-Day plan includes specific budget allocation and content selection?

Entity Health Snapshot includes actionable next steps?

Case study drafted and ready for publishing?

Client signed off on all deliverables?

CRM updated with final status?

Common Pitfalls

Accepting clients who don't meet qualification gate → enforce $100k+/mo, 100+ reviews, willing to film. Misfits go to LSS $300 tier

Scope creep inside the Sprint → all custom requests go to Phase 2 list. No exceptions

Client delays killing the 30-day timeline → document delays immediately, pause clock with written notice

Skipping the case study → "If it's not published, it's not done." Build case study creation into Day 27-30

Paying comp without CRM evidence → require lead source, call notes, proposal, signature before releasing sales commission

QA bonus released despite defects → zero critical defects means zero. Hold the standard

Canon Compliance

Canon source: 02-content-factory-process.md (Sprint compresses the full Content Factory into 30 days: interview = Produce, articles/videos = Process, distribution plan = Promote); 06-topic-wheel.md (entity-first site architecture maps to Topic Wheel structure)

Triangles served: CCS — the Sprint IS a fixed checklist with defined software stack (WordPress, schema.org, Dollar-a-Day); ACC — deliverables span Awareness (citations, entity foundations), Consideration (authority articles, short-form videos), Conversion (personal brand site with CTAs, distribution plan); GCT — qualification gate defines Goals ($100k+/mo revenue), Content (willing to film), Targeting (LSA category business)

Human checkpoints: Qualification gate (human reviews revenue, reviews, willingness to film); client interview (60 min recorded); client approval of copy; client sign-off on all deliverables; Dennis approves compensation exceptions; QA passes before handoff

Anti-vandalism: Fixed scope with zero custom detours (extras go to Phase 2 list); qualification gate prevents misfits; 50/50 payment terms protect cash flow; QA/On-Time Bonus Pool only released with zero critical defects; CRM evidence required for sales commission; every Sprint must produce a published case study

Last audited: 2026-03-20 (BlitzMetrics Canon Alignment run)

Learnings Log

[Empty — gets populated as Claude learns from execution]